## Artifacts and Data Elements
Artifact Name | Data Element
02 Accounting/Fiscal Calendar | A Accounting month dates
02 Accounting/Fiscal Calendar | B Beginning of period (BOP) dates
02 Accounting/Fiscal Calendar | C End of period (EOP) dates
03 EVM System Description | A High value/critical material categorization process
03 EVM System Description | B Internal replanning parameters
03 EVM System Description | C Permitted applications of MR
03 EVM System Description | D Permitted baseline changes during freeze period
03 EVM System Description | E Permitted changes to open WPs
03 EVM System Description | F Permitted EVTs for material
03 EVM System Description | G Permitted UB transactions
03 EVM System Description | H Planning window/freeze period
03 EVM System Description | J PMB incorporation timeframe
03 EVM System Description | K Process for incorporating indirect rates into budgets
03 EVM System Description | L Process for incorporating subcontractor/supplier MR
03 EVM System Description | M Requirements for EAC risk/opportunity incorporation
03 EVM System Description | N UB distribution timeframe
03 EVM System Description | P Variance analysis thresholds
03 EVM System Description | Q WBS reporting level requirements
03 EVM System Description | R Indirect Cost Management Organization
03 EVM System Description | S VAR requirements
03 EVM System Description | T Freeze period baseline change exceptions
03 EVM System Description | U Guidance on EVTs
03 EVM System Description | V Process for LOE/discrete work decomposition
03 EVM System Description | W CEAC Process/Requirements
04 Contract Statement of Work | A Contractual milestones
04 Contract Statement of Work | B SOW paragraphs
05 Contract Work Breakdown Structure Dictionary | A SOW references
06 Contractual Documents | A Contracts requiring EVMS
06 Contractual Documents | B Contractual milestones
06 Contractual Documents | C Contractual and/or CLIN Period of Performance (PoP)
06 Contractual Documents | D Requirement to report recurring/non-recurring costs
06 Contractual Documents | E Requirement to report unit or lot costs
06 Contractual Documents | F Subcontractor/Supplier EVMS flow-down requirements
06 Contractual Documents | G Contractual mods (authorization dates)
06 Contractual Documents | H Contractual mods adding/removing scope
07 Organization Breakdown Structure | A OBS elements
08 Control Account Plans | A Element of Cost (material)
09 Work Authorization Documentation (WAD) | A Approval date
09 Work Authorization Documentation (WAD) | B BAC
09 Work Authorization Documentation (WAD) | C Baseline Finish Date
09 Work Authorization Documentation (WAD) | D Baseline Start Date
09 Work Authorization Documentation (WAD) | E Current/previous CA BAC
09 Work Authorization Documentation (WAD) | F Period of Performance (PoP)
09 Work Authorization Documentation (WAD) | G Scope description
10 Integrated Master Plan | A IMP code
10 Integrated Master Plan | B Summary tasks
11 Integrated Master Schedule (IMS) | A Actual Finish Date
11 Integrated Master Schedule (IMS) | AA Leads
11 Integrated Master Schedule (IMS) | AB OBS elements
11 Integrated Master Schedule (IMS) | AC Planning Package UIDs
11 Integrated Master Schedule (IMS) | AD Predecessors
11 Integrated Master Schedule (IMS) | AE Predecessor (Type)
11 Integrated Master Schedule (IMS) | AF Remaining Duration
11 Integrated Master Schedule (IMS) | AG Status Date
11 Integrated Master Schedule (IMS) | AH Subcontractor/Supplier ID
11 Integrated Master Schedule (IMS) | AJ Successors
11 Integrated Master Schedule (IMS) | AK Successor (Type)
11 Integrated Master Schedule (IMS) | AL Summary Task UIDs
11 Integrated Master Schedule (IMS) | AM Task/Activity/Milestone UIDs
11 Integrated Master Schedule (IMS) | AN WBS elements
11 Integrated Master Schedule (IMS) | AP WP/PP/SLPP UIDs
11 Integrated Master Schedule (IMS) | AQ Duration/Forecast Duration
11 Integrated Master Schedule (IMS) | AR CA UIDs
11 Integrated Master Schedule (IMS) | B Actual Finish Date (prior month)
11 Integrated Master Schedule (IMS) | C Actual Start Date
11 Integrated Master Schedule (IMS) | D Actual Start Date (prior month)
11 Integrated Master Schedule (IMS) | E Approved risk mitigation activities
11 Integrated Master Schedule (IMS) | F Baseline Duration
11 Integrated Master Schedule (IMS) | G Baseline Finish Date
11 Integrated Master Schedule (IMS) | H Baseline Finish Date (period to period comparison)
11 Integrated Master Schedule (IMS) | J Baseline Start Date
11 Integrated Master Schedule (IMS) | K Baseline Start Date (period to period comparison)
11 Integrated Master Schedule (IMS) | L BCWS (time-phasing)
11 Integrated Master Schedule (IMS) | M Beginning of period (BOP) dates
11 Integrated Master Schedule (IMS) | N Constraint Date
11 Integrated Master Schedule (IMS) | P Constraint Method Critical Path Activities
11 Integrated Master Schedule (IMS) | Q Constraint Type
11 Integrated Master Schedule (IMS) | R Contractual milestones
11 Integrated Master Schedule (IMS) | S End of period (EOP) dates
11 Integrated Master Schedule (IMS) | T EV % complete
11 Integrated Master Schedule (IMS) | U EVT
11 Integrated Master Schedule (IMS) | V Forecast Finish Date
11 Integrated Master Schedule (IMS) | W Forecast Start Date
11 Integrated Master Schedule (IMS) | X Total Float/Slack
11 Integrated Master Schedule (IMS) | Y IMP code
11 Integrated Master Schedule (IMS) | Z Lags
12 Program Critical Path | A Program Critical Path Activities
12 Program Critical Path | B Near-Critical Path Activities
12 Program Critical Path | C Driving Path Activities
13 EV Cost Tool Data | A Monthly overhead cost accumulation (by overhead pool)
13 EV Cost Tool Data | AA CA UIDs
13 EV Cost Tool Data | AB CAM assignment
13 EV Cost Tool Data | AC CPICUM (derived)
13 EV Cost Tool Data | AD Cumulative Cost Variance
13 EV Cost Tool Data | AE Cumulative Schedule Variance
13 EV Cost Tool Data | AF Current Cost Variance
13 EV Cost Tool Data | AG Current Schedule Variance
13 EV Cost Tool Data | AH EAC
13 EV Cost Tool Data | AJ Element of Cost
13 EV Cost Tool Data | AK Element of Cost (material)
13 EV Cost Tool Data | AL ETC
13 EV Cost Tool Data | AM ETC (time-phased)
13 EV Cost Tool Data | AN EV % complete
13 EV Cost Tool Data | AP EVT
13 EV Cost Tool Data | AQ Indirect rate table
13 EV Cost Tool Data | AR MR
13 EV Cost Tool Data | AS OBS elements
13 EV Cost Tool Data | AT Planning Package UIDs
13 EV Cost Tool Data | AU Subcontractor/Supplier ID
13 EV Cost Tool Data | AV Subcontractor/Supplier MR
13 EV Cost Tool Data | AW TCPIEAC (derived)
13 EV Cost Tool Data | AX UB
13 EV Cost Tool Data | AY Variance at Complete
13 EV Cost Tool Data | AZ WBS elements
13 EV Cost Tool Data | B Unburdened and burdened cost
13 EV Cost Tool Data | BA WP/PP/SLPP UIDs
13 EV Cost Tool Data | BB BCWPCUR (monthly historical)
13 EV Cost Tool Data | C ACWPCUM
13 EV Cost Tool Data | D ACWPCUM (current and prior month)
13 EV Cost Tool Data | E ACWPCUR
13 EV Cost Tool Data | EB ACWPCUR (monthly historical)
13 EV Cost Tool Data | F ACWPCUR (non-material)
13 EV Cost Tool Data | G ACWPCUR (of selected months)
13 EV Cost Tool Data | H BAC
13 EV Cost Tool Data | J BAC for CA
13 EV Cost Tool Data | K BAC for CA/SLPP
13 EV Cost Tool Data | L BAC for WP (current and prior month)
13 EV Cost Tool Data | M BAC for WP/PP
13 EV Cost Tool Data | N Baseline Finish Date
13 EV Cost Tool Data | P Baseline Start Date
13 EV Cost Tool Data | Q BCWPCUM
13 EV Cost Tool Data | R BCWPCUM (current and prior month)
13 EV Cost Tool Data | S BCWPCUR
13 EV Cost Tool Data | T BCWPCUR (non-material)
13 EV Cost Tool Data | U BCWS (time-phasing)
13 EV Cost Tool Data | V BCWSCUM
13 EV Cost Tool Data | W BCWSCUM (current and prior month)
13 EV Cost Tool Data | X BCWSCUR
13 EV Cost Tool Data | Y BCWSCUR for CA
13 EV Cost Tool Data | Z BCWSCUR for WP and PP
14 Accounting System Data | A Capability to report recurring/non-recurring costs
14 Accounting System Data | B Capability to report unit or lot costs
14 Accounting System Data | C Contract level cumulative actual direct costs
14 Accounting System Data | E Direct/indirect rates
14 Accounting System Data | F Indirect rates (rate table)
14 Accounting System Data | G Material transfers/loans
14 Accounting System Data | H Contract Level Cumulative Actual Indirect Costs
15 Internal Variance Analysis Thresholds | A Internal variance analysis thresholds
16 Internal Variance Analysis Reports | A VARs
17 Variance Analysis Reports (VARs) | A Indirect VARs
17 Variance Analysis Reports (VARs) | B Price Variance (PV) formula
17 Variance Analysis Reports (VARs) | C Usage Variance (UV) formula
17 Variance Analysis Reports (VARs) | D VARs
17 Variance Analysis Reports (VARs) | E Rate Variance (RV) Formula
17 Variance Analysis Reports (VARs) | F Volume Variance (VV) Formula
18 Baseline Control Logs | A Baseline changes (effective dates)
18 Baseline Control Logs | B Baseline changes (selected)
18 Baseline Control Logs | C Baseline changes involving budget distributions
18 Baseline Control Logs | D Baseline changes involving UB transactions
18 Baseline Control Logs | E Budget change values
18 Baseline Control Logs | F CBB
18 Baseline Control Logs | G Date of contractual mod incorporation into PMB
18 Baseline Control Logs | H OTB budget
18 Baseline Control Logs | J PMB change
18 Baseline Control Logs | K UB
18 Baseline Control Logs | L UB distributions
19 Corrective Action Log | A Corrective action log entries
19 Corrective Action Log | B Corrective action log status date
19 Corrective Action Log | C Estimated completion dates (open corrective actions)
20 IPMR/CPR | A Format 1 BCWSCUM
20 IPMR/CPR | B Format 1 BCWSCUR
20 IPMR/CPR | C Format 1 current period MR
20 IPMR/CPR | D Format 1 current period UB
20 IPMR/CPR | E Format 1 Date of OTB/OTS
20 IPMR/CPR | F Format 1 EACs (Best, Worst, Most Likely)
20 IPMR/CPR | G Format 1 lowest reporting-level WBS elements
20 IPMR/CPR | H Format 1 LRE
20 IPMR/CPR | J Format 1 MR
20 IPMR/CPR | K Format 1 PMB
20 IPMR/CPR | L Format 1 previous period MR
20 IPMR/CPR | M Format 1 previous period UB
20 IPMR/CPR | N Format 1 TAB
20 IPMR/CPR | P Format 1 UB
20 IPMR/CPR | Q Format 2 OBS elements
20 IPMR/CPR | R Format 3 beginning of period BCWS
20 IPMR/CPR | S Format 3 PMB net change (derived)
20 IPMR/CPR | T Format 5 EAC rationale
20 IPMR/CPR | U Format 5 VARs
20 IPMR/CPR | V Format 5 VARs requiring corrective actions
20 IPMR/CPR | W Format 5 IMS discussion of schedule margin
20 IPMR/CPR | X Format 1 CBB
20 IPMR/CPR | Y Format 1 NCC
20 IPMR/CPR | Z Format 1 AUW
20 IPMR/CPR | AA Format 1 OTB/reprogramming budget
21 List of Major Subcontractors/Suppliers | A Subcontractors/Suppliers and Intra-organizational elements
22 Subcontractor/Supplier IPMR/CPR | A ACWPCUM
22 Subcontractor/Supplier IPMR/CPR | B BAC
22 Subcontractor/Supplier IPMR/CPR | C BCWPCUM
22 Subcontractor/Supplier IPMR/CPR | D BCWSCUM
22 Subcontractor/Supplier IPMR/CPR | E Subcontractor/Supplier MR
22 Subcontractor/Supplier IPMR/CPR | F ACWPCUR
22 Subcontractor/Supplier IPMR/CPR | G BCWPCUR
22 Subcontractor/Supplier IPMR/CPR | H BCWSCUR
23 CAS Disclosure Statement | A Indirect cost pools
23 CAS Disclosure Statement | B Method of application of indirect rates to direct costs
23 CAS Disclosure Statement | C Indirect Cost Management Authority/Responsibility
23 CAS Disclosure Statement | D Process for updating and applying indirect rates
24 FPRA/FPRP (or published rates) | A Direct/indirect rates
24 FPRA/FPRP (or published rates) | B Overhead categories/departments
24 FPRA/FPRP (or published rates) | C Published indirect rates
25 Customer Approval for OTB | A OTB approval
25 Customer Approval for OTB | B OTB budget
28 Risk & Opportunities Log/Register | A Approved risk mitigation activities
28 Risk & Opportunities Log/Register | B Factored risks/opportunities
29 MRP/ERP System Data | A Material items issued to contract
29 MRP/ERP System Data | B Material transfers/loans
29 MRP/ERP System Data | C Material Need dates based on Material Category
32 Quantifiable Backup Data | A EV % complete
32 Quantifiable Backup Data | B QBD Steps and Weights
33 Comprehensive EAC Documentation | A CEAC commencement and completion dates
36 Program Detail Schedules | A Baseline Finish Date
36 Program Detail Schedules | B Baseline Start Date
36 Program Detail Schedules | C Forecast Finish Date
36 Program Detail Schedules | D Forecast Start Date
36 Program Detail Schedules | E Actual Start Date
36 Program Detail Schedules | F Actual Finish Date
37 Subcontractor/Supplier Schedule (IMS) | A Baseline Finish Date
37 Subcontractor/Supplier Schedule (IMS) | B Baseline Start Date
37 Subcontractor/Supplier Schedule (IMS) | C Forecast Finish Date
37 Subcontractor/Supplier Schedule (IMS) | D Forecast Start Date
37 Subcontractor/Supplier Schedule (IMS) | E Actual Start Date
37 Subcontractor/Supplier Schedule (IMS) | F Actual Finish Date
37 Subcontractor/Supplier Schedule (IMS) | G Task/Milestone UIDs
38 Contract WBS | A Lowest reporting-level WBS elements
39 Organizational Charts | A Indirect Cost Management Organization
39 Organizational Charts | B OBS elements
41 Budget Log | A Baseline changes
41 Budget Log | B CBB/TAB changes (effective dates)
41 Budget Log | C Current period MR changes
41 Budget Log | D Current period UB changes
41 Budget Log | E Current/previous CA BAC
41 Budget Log | F MR
41 Budget Log | G MR transactions
41 Budget Log | H Scope description
41 Budget Log | J UB
41 Budget Log | K UB transactions
43 Baseline Change Request | A Baseline change substantiation
43 Baseline Change Request | B Baseline Finish Date
43 Baseline Change Request | C Baseline Start Date
43 Baseline Change Request | D Budget change values
43 Baseline Change Request | E MR transaction substantiation
43 Baseline Change Request | F Scope description
43 Baseline Change Request | G UB transaction substantiation
46 IPMR/CPR CDRL | A VAR thresholds/requirements
46 IPMR/CPR CDRL | B WBS reporting level requirements
49 Estimated Actuals Reconciliation | A Estimated actual costs
49 Estimated Actuals Reconciliation | B Estimated actual costs (supporting documentation)
50 Cost Tool Calendar | A Beginning of period (BOP) dates
50 Cost Tool Calendar | B End of period (EOP) dates
52 EVMS Analysis Tool Data | A Cumulative Cost Variance
52 EVMS Analysis Tool Data | B Cumulative Schedule Variance
52 EVMS Analysis Tool Data | C Current Cost Variance
52 EVMS Analysis Tool Data | D Current Schedule Variance
52 EVMS Analysis Tool Data | E Variance at Complete
53 Resource Plans | A ETC (time-phased)
54 Actual Cost Reconciliation | A Actual cost reconciliation
55 BOM | A Material items issued to contract
56 CSDR | A Lowest reporting-level WBS elements
57 Customer Approval for OTS | A OTS approval
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | A Baseline Finish Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | B Baseline Start Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | C Forecast Finish Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | D Forecast Start Date
59 RAM | A CAM assignment
60 Letter of Accounting System Approval from ACO or other cognizant authority | A Accounting System Approval
61 Letter of MMAS Approval from ACO or other cognizant authority | A MMAS Approval

## Artifact Descriptions
Data Item List All data are required in electronic format. PDF files are not considered electronic format, unless they are used to improve data or augment information (such as hand-writing, additional comments, and/or signatures). Please provide data in a file structure using the outline given below with descriptive file names. Provide subfolders for each contract with each maintaining the sequence given below. Artifact names and numbers can change over time so please review the data prior to submittal.
Request Date: |  | Requested Data Delivery Date:
Artifact # | Artifact Name | Artifact Description | Periodicity
01 | Program Summary Data | For each program provide the below items in one excel file
Integrated Master Plan (IMP) on Contract? (Yes/No)
# of IMP Codes
Freeze Period (i.e. 60 days)
Number of Work Packages (WP)
Number of Control Accounts (CA)
02 | Accounting Fiscal Calendar | Fiscal Calendar Used (include all accounting periods from beginning of program until program completion)
03 | EVM System Description | System Descriptions, corporate operating instructions, standard operating procedures, and program unique directives/procedures. (Include the latest approved versions)
04 | Contract Statement of Work | Contract Statement of Work
05 | Contract Work Breakdown Structure Dictionary | Contract Work Breakdown Structure Dictionary. Include reference ID to the SOW.
06 | Contractual Documents | Initial contract, and contract modifications since program inception, e.g., contract modification, letter to proceed from contracts office or legal office, not-to-exceed letter, change order, engineering change order, delivery order, basic ordering agreement, etc.
Comprehensive list by date, dollar value, funding and changes to the contract target cost.
Electronic copies of all contract mods for the last 12 months.
07 | Organization Breakdown Structure | Provide in organization chart form, to include OBS codes which align to those in RAM, as well as names of personnel responsible for each organizational function who have authority to commit resources. OBS also needs to include major subcontractors/suppliers.
08 | Control Account Plan (CAP) | Control Account Plans (CAP) by element of cost (i.e., labor hours and dollars, material dollars and other direct cost dollars) and their associated burdens and overhead costs. Must include any Summary Level Planning Packages (SLPPs). Provide these CAPs in the form of an excel export.
09 | Work Authorization Documentation (WAD) | Work Authorization Documents for entire program.
10 | Integrated Master Plan (IMP) | Integrated Master Plan (IMP) if on Contract.
11 | Integrated Master Schedule (IMS) | Integrated Master Schedule including summary, intermediate and detailed schedules. Provide backups directly from the scheduling tool (native format).
12 | Program Critical Path | Provide the program latest critical path. Include a list of the settings used during the critical path calculation including the status date, calendar and any calculation options that could impact how the tool calculates critical path. Also, include critical path procedure(s) and/or references to critical path procedure(s) in system description (or other applicable documents)
13 | EV Cost Tool Data | Data shall be provided for all reporting periods from contract start and include all records down to the work package level. The data must include unique identifier(s) that allows for control account and work package comparison. Dollars ($s), thousands of dollars (K$s) or hours must be identified as such. In addition to the data export, provide a data dictionary for all codes used in the requested fields.
Unique ID
Control account ID
Work package ID
Planning package and work package indicator (e.g., PP, WP, SLPP)
Description
WBS
OBS
Subcontractor/Supplier ID/Name
CAM name
Earned Value Technique (EVT)
Element of Cost (EOC)
Reporting period (month and year)
Baseline Start
Baseline Finish
|  | Actual Start | Monthly
|  | Actual Finish | Annual
|  | Forecast Start | Quarterly
|  | Forecast Finish | Annual
|  | Current BCWS | Annual
|  | Current BCWP | Monthly
Current ACWP
CUM BCWS
CUM BCWP
CUM ACWP
BAC
EAC
ETC
Current Cost Variance
Current Schedule Variance
Cumulative Cost Variance
Cumulative Schedule Variance
Variance at Complete
14 | Accounting System Data | See specific testing information
15 | Internal Variance Analysis Thresholds | Internal variance analysis thresholds
16 | Internal Variance Analysis Reports | Internal Variance Analysis Reports (VARs)
17 | Variance Analysis Reports (VARs) | Variance Analysis Reports (VARs) (Direct/Indirect)
18 | Baseline Control Logs | Baseline Control Logs
Management Reserve (MR)
Undistributed Budget (UB)
Performance Measurement Baseline (PMB) and/or Contract Budget Base (CBB)
19 | Corrective Action Log | Corrective Action Tracking System Log or database
20 | IPMR/CPR | Integrated Program Management Report (IPMR)/Contract Performance Report (CPR)
Format 1
Format 2
Format 3
Format 5
21 | List of Major Subcontractors/Suppliers | List of Major Subcontractors/Suppliers & intra-organizational elements w/EVMS flow down
22 | Subcontractor/Supplier IPMR/CPR | Subcontractor/Supplier IPMR/CPR (All Formats)
23 | CAS Disclosure Statement | CAS Disclosure Statement and any applicable policies and procedures, desk instructions, etc., addressing the accounting process
24 | FPRA/FPRP (or published rates) | Forward Pricing Rate documentation, at time of program baseline, last OTB - if applicable, and start of current fiscal year. (Provide most recent FPRA, FPRP being utilized.)
25 | Customer Approval for OTB
26 | CBAR - MMAS, Accounting System Status
27 | CFSR
28 | Risk & Opportunities Log/Register
29 | MRP/ERP System Data
32 | Quantifiable Backup Data
33 | Comprehensive EAC Documentation
34 | Mapping of EVMS Data from Sub to Prime
35 | Intermediate Schedules
36 | Program Detail Schedules
37 | Subcontractor/Supplier Schedule (IMS)
38 | Contract WBS
39 | Organizational Charts
40 | Program WBS
41 | Budget Log
42 | wInsight Data (or equivalent) | wInsight .wsa files (entire program at lowest level produced from cost tool).
43 | Baseline Change Request | or equivalent Baseline Change Documentation
44 | Cost Data Dictionary
45 | IMS Data Dictionary
46 | IPMR/CPR CDRL
47 | IMS CDRL
48 | CAS Disclosure Statement Approval
49 | Estimated Actuals Reconciliation | To include supporting documentation (eg, invoices, emails, subcontractor CPR)
50 | Cost Tool Calendar
51 | LOE Justification
52 | EVMS Analysis Tool Data
53 | Resource Plans
54 | Actual Cost Reconciliation
55 | BOM
56 | CSDR
57 | Customer Approval for OTS
58 | Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System)
59 | RAM
60 | Letter of Accounting System Approval from ACO or other cognizant authority
61 | Letter of MMAS Approval from ACO or other cognizant authority

## Revision History
EVMS Surveillance Metrics Revision History
Version Date | Revision Description
2019-01-28 | Updated for Nov 2018 CCB meeting results. Seven new metrics added, specific metric changes implemented, and all metrics affected by global changes thereby resulting in all metrics changing to version 3.1.
2019-02-19 | Updated to add BP number and BP4 group number columns and tabs. Assigned BP4 group numbers to the 7 new metrics resulting from the Nov 2018 CCB. Fixed X value on 03A101e to match spec sheet. Added this "Revision History" tab and "Metrics Breakdown" tab.
2019-02-21 | BP3 tab was missing three metrics.
2019-03-01 | Updated Artifact 13 description to include the phrase: "for all reporting periods from contract start and include all records..." Added Artifact 13 data element "AA BCWPCUR (monthly historical)." Updated 44 metrics to version 3.2 - includes 4 new metrics (16A501c [GP1], 16A501d [GP1], 21A302c [GP1], 21A302d [GP1]), and 2 metrics were deleted (06A204a [GP1] & 06A213a [GP1]) for a new metrics total of 139. All tabs updated accordingly.
2019-05-24 | Updated Artifact 13 data element "AA BCWPCUR (monthly historical)" to "BB BCWPCUR (monthly historical)" due to an error in duplicating the "AA" identifier with another element ("AA CA UIDs"). Added data elements: 03W - CEAC Process/Requirements (ref 27A101b), 17E Rate Variance (RV) Formula (ref 23A201a), 17F Volume Variance (VV) Formula (ref 23A201a). Changes to 46 metrics - includes 6 new metrics (08I101a [BP3&4 GP1], 08I102a [BP4 GP1], 08I103a [BP4 GP1], 10I101a [BP3&4 GP3]), 27I101a [BP3&4 GP1], 27I201a [BP3&4 GP1]),and 2 metrics were deleted (10A301a [BP4 GP3], 27A104a [BP4, GP1]) for a new metrics total of 143. All 143 metrics updated to version 3.3 even if there were no changes; updating all metrics to the newest version number will be the process going forward. Added column F for ease of identifying metrics that experienced an actual change since the most recent CCB. All tabs updated accordingly.
2019-08-31 | Changes to 105 metrics - added 1 metric (19A401a [BP4], 3 metrics were deleted (06A203a [BP3&4], 06A206a [BP3&4] and 19A301a [BP4]) for a new metrics total of 141. All 141 metrics updated to version 3.4 even if there were no changes; updating all metrics to the newest version number will be the process going forward. BP4 will no longer contain metric groups. Renamed Column D on EVMS Metrics Tracker tab from BP4 Group to GL. Deleted tabs "BP4 Group1", "BP4 Group2", "BP4 Group3", "BP4 Group4", BP4 Group5". Deleted BP4 groupings from Metrics Breakdown tab. All tabs updated accordingly.
2019-09-10 | Change to one metric, 16A501a. Updated to v3.4.1
2020-01-23 | Change to 45 Metrics. 3 Metrics deleted (10A109a, 10I101a, and 22I101a).
2020-03-26 | Changes to 06A506b, 06A506c, and 27A102a
2020-07-29 | Change to 33 metrics. 5 metrics added (27A102b, 29I402a, 29I402b, 29I402c, 29I402d)
2020-11-02 | Changes to 24 metrics as interim release (v3.6.1). Unchanged metrics remain version v3.6.
2021-03-05 | Changes to 17 metrics. One metric deleted. All metrics were updated to v4.0. Release 4.0 included changes to DECM template and updates to wording and formatting for consistency between the DECM. Tracker was updated to include new column "M" identifying any metric that requires sampling.