## Assumptions
Costs are in whole dollars.
Costs are in total dollars (e.g., overhead, General & Administrative and Cost of Money are included).
The accounting periods are equal to calendar months.
The freeze period is the current period and next period.
The following Earned Value Techniques (EVTs) are used: 0/100 50/50 Level of Effort (LOE) Percent Complete (% Complete) 100/0 Milestones Expert Judgment
The following Elements of Cost (EOCs) are used: Labor Material Other Direct Costs Subcontractor
Planning Packages (PPs) and Summary Level Planning Packages (SLPPs) are denoted in the EVT field.

## Cost Data Dictionary
Field | Explanation
WBS | Work Breakdown Structure (numerical value)
OBS | Organizational Breakdown Structure (alphabetical value)
CA ID | Control Account ID (WBS + OBS, e.g., 1A) SLPPs have no OBS (e.g., the first SLPP is 1)
WP ID | Work Package ID (CA ID + numerical value, e.g., 1A1)
EVT | PP = Planning Package SLPP = Summary Level Planning Package 0/100 = 0/100 WP 50/50 = 50/50 WP LOE = Level of Effort WP % Complete = Percent Complete WP 100/0 = 100/0 WP Milestones = Milestones WP Expert Judgement = Expert Judgment WP Blank = missing EVT WP
Accounting Period | Last day of calendar month (accounting periods are calendar months)
EOC | Blank = missing EOCs for WPs
CAM | SLPPs do not have CAM assignments, other blanks are missing CAM assignments
BCWS | Time-phased BCWS
BCWP | Time-phased BCWP
ACWP | Time-phased ACWP
ETC | Time-phased ETC-only, not EAC

## IMS Data Dictionary - Project
Field | Explanation
Unique ID | Unique ID that is consistent between months.
Name | Milestones and SVTs have associated names, otherwise blank
CA ID (Text1) | Control Account ID (WBS + OBS, e.g., 1A) SLPPs have no OBS (e.g., the first SLPP is 1)
WP ID (Text2) | Work Package ID (CA ID + numerical value, e.g., 1A1)
CWBS (Text5) | Work Breakdown Structure (numerical value)
OBS (Text4) | Organizational Breakdown Structure (alphabetical value)
EVT (Text3) | PP = Planning Package activity SLPP = Summary Level Planning Package activity 0/100 = 0/100 WP activity 50/50 = 50/50 WP activity LOE = Level of Effort WP activity % Complete = Percent Complete WP activity 100/0 = 100/0 WP activity Milestones = Milestones WP activity Expert Judgement = Expert Judgment WP activity MS = milestone SVT = schedule visibility task activity Blank = summary tasks (excluding one WP to many activities summary tasks) or missing EVT WPs
EV % Complete (Text6) | Intended to tie to cost % complete (i.e., BCWPcum/BAC) When there is one WP to many activities, the summary task for the WP should tie to the cost % complete
Baseline Start | Baseline start date field
Baseline Finish | Baseline finish date field
Start | Forecast start date field
Finish | Forecast finish date field
Actual Start | Actual start date field
Actual Finish | Actual finish date field

## IMS Data Dictionary - Open Plan
Custom View | Artificial Dataset
Field | Explanation
Unique ID ((S) MSPUNIQUEID) | Unique ID that is consistent between months
Activity Desc. ((S) DESCRIPTION) | Milestones and SVTs have associated names, otherwise blank
CA ID ((U) USER_CHR01) | Control Account ID (WBS + OBS, e.g., 1A) SLPPs have no OBS (e.g., the first SLPP is 1)
WP ID ((U) USER_CHR02) | Work Package ID (CA ID + numerical value, e.g., 1A1)
WBS ((U) USER_CHR05) | Work Breakdown Structure (numerical value)
OBS ((U) USER_CHR04) | Organizational Breakdown Structure (alphabetical value)
EVT ((U) USER_CHR03) | PP = Planning Package activity SLPP = Summary Level Planning Package activity 0/100 = 0/100 WP activity 50/50 = 50/50 WP activity LOE = Level of Effort WP activity % Complete = Percent Complete WP activity 100/0 = 100/0 WP activity Milestones = Milestones WP activity Expert Judgement = Expert Judgment WP activity MS = milestone SVT = schedule visibility task activity Blank = summary tasks (excluding one WP to many activities summary tasks) or missing EVT WPs
EV % Complete ((U) USER_CHR06) | Intended to tie to cost % complete (i.e., BCWPcum/BAC) When there is one WP to many activities, the summary task for the WP should tie to the cost % complete
Baseline Start ((S) BSDATE) | Baseline start date field
Baseline Finish ((S) BFDATE) | Baseline finish date field
Early Start ((S) ESDATE) | Forecast start date field
Early Finish ((S) EFDATE) | Forecast finish date field
Actual Start ((S) ASDATE) | Actual start date field
Actual Finish ((S) AFDATE) | Actual finish date field

## IMS Data Dictionary - Primavera
Custom Layout | Artificial Datasets
Field | Explanation
Unique ID (MSP Activity ID) | Unique ID that is consistent between months
Activity Name | Milestones and SVTs have associated names, otherwise "x" since Primavera does not allow the Activity Name to be blank
CA ID | Control Account ID (WBS + OBS, e.g., 1A) SLPPs have no OBS (e.g., the first SLPP is 1)
WP ID | Work Package ID (CA ID + numerical value, e.g., 1A1)
CWBS | Work Breakdown Structure (numerical value)
OBS | Organizational Breakdown Structure (alphabetical value)
EVT | PP = Planning Package activity SLPP = Summary Level Planning Package activity 0/100 = 0/100 WP activity 50/50 = 50/50 WP activity LOE = Level of Effort WP activity % Complete = Percent Complete WP activity 100/0 = 100/0 WP activity Milestones = Milestones WP activity Expert Judgement = Expert Judgment WP activity MS = milestone SVT = schedule visibility task activity Blank = summary tasks (excluding one WP to many activities summary tasks) or missing EVT WPs
EV % Complete | Intended to tie to cost % complete (i.e., BCWPcum/BAC) When there is one WP to many activities, the summary task for the WP should tie to the cost % complete
BL Project Start | Baseline start date field
BL Project Finish | Baseline finish date field
Start | Forecast start date field
Finish | Forecast finish date field
Actual Start | Actual start date field
Actual Finish | Actual finish date field