## IPMR Data
Negotiated Contract Cost (IPMR Format 1 block 5.b) | 110000000
Authorized Unpriced Work (IPMR Format 1 block 5.c) | 0
Undistributed Budget (UB) Budget at Completion (BAC) (IPMR Format 1 block 8.d.(14)) | 5000000
UB Estimate at Completion (IPMR Format 1 block 8.d.(15)) | 5000000
Subtotal/Performance Measurement Baseline BAC (IPMR Format 1 block 8.e.(14)) | 100000000
Management Reserve BAC (IPMR Format 1 block 8.f.(14)) | 10000000
Over-Target Budget Value (IPMR Format 1 block 8.g.(13)) | 0
Total Allocated Budget (IPMR Format 1 block 8.g.(14)) | 110000000

## Budget Log
UB | 5000000
MR | 10000000

## Cost Data
WBS | OBS | CA ID | WP ID | EVT | Accounting Period | EOC | CAM | BCWS | BCWP | ACWP | ETC
1 |  | 1 |  | SLPP | 2020-02-29 | Labor |  | 25000.001 | 0.001 | 0.001 | 25000.001
1 |  | 1 |  | SLPP | 2020-02-29 | Material |  | 100000.001 | 0.001 | 0.001 | 100000.001
1 |  | 1 |  | SLPP | 2020-03-31 | Labor |  | 37500.001 | 0.001 | 0.001 | 37500.001
1 |  | 1 |  | SLPP | 2020-03-31 | Other Direct Costs |  | 5000.001 | 0.001 | 0.001 | 5000.001
1 |  | 1 |  | SLPP | 2020-04-30 | Labor |  | 50000.001 | 0.001 | 0.001 | 50000.001
1 |  | 1 |  | SLPP | 2020-04-30 | Material |  | 250000.001 | 0.001 | 0.001 | 250000.001
1 |  | 1 |  | SLPP | 2020-05-31 | Labor |  | 37500.001 | 0.001 | 0.001 | 37500.001
1 |  | 1 |  | SLPP | 2020-05-31 | Other Direct Costs |  | 5000.001 | 0.001 | 0.001 | 5000.001
1 |  | 1 |  | SLPP | 2020-06-30 | Labor |  | 25000.001 | 0.001 | 0.001 | 25000.001
1 |  | 1 |  | SLPP | 2020-06-30 | Material |  | 500000.001 | 0.001 | 0.001 | 500000.001
2 |  | 2 |  | SLPP | 2020-02-29 | Material |  | 500000.001 | 0.001 | 0.001 | 500000.001
2 |  | 2 |  | SLPP | 2020-04-30 | Material |  | 250000.001 | 0.001 | 0.001 | 250000.001
2 |  | 2 |  | SLPP | 2020-05-31 | Material |  | 250000.001 | 0.001 | 0.001 | 250000.001
2 |  | 2 |  | SLPP | 2020-08-31 | Material |  | 500000.001 | 0.001 | 0.001 | 500000.001
4 |  | 4 |  | SLPP | 2020-02-29 | Labor |  | 1250000.001 | 0.001 | 0.001 | 1250000.001
4 |  | 4 |  | SLPP | 2020-02-29 | Material |  | 2500000.001 | 0.001 | 0.001 | 2500000.001
4 |  | 4 |  | SLPP | 2020-02-29 | Other Direct Costs |  | 125000.001 | 0.001 | 0.001 | 125000.001
4 |  | 4 |  | SLPP | 2020-02-29 | Subcontractor |  | 5000000.001 | 0.001 | 0.001 | 5000000.001
4 |  | 4 |  | SLPP | 2020-03-31 | Labor |  | 1250000.001 | 0.001 | 0.001 | 1250000.001
4 |  | 4 |  | SLPP | 2020-03-31 | Material |  | 2500000.001 | 0.001 | 0.001 | 2500000.001
4 |  | 4 |  | SLPP | 2020-03-31 | Other Direct Costs |  | 125000.001 | 0.001 | 0.001 | 125000.001
4 |  | 4 |  | SLPP | 2020-03-31 | Subcontractor |  | 5000000.001 | 0.001 | 0.001 | 5000000.001
1 | A | 1A | 1A1 | 0/100 | 2019-11-30 | Material | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A2 | 50/50 | 2019-11-30 | Material | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A2 | 50/50 | 2019-12-31 | Material | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-05-31 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-06-30 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-07-31 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-08-31 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-09-30 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A3 | % Complete | 2019-10-31 | Labor | CAM A | 50000.001 | 50000.001 | 0.001 | 0.001
1 | A | 1A | 1A4 | % Complete | 2019-10-31 | Material | CAM A | 625000.001 | 625000.001 | 0.001 | 0.001
1 | A | 1A | 1A4 | % Complete | 2019-12-31 | Material | CAM A | 75000.001 | 75000.001 | 0.001 | 0.001
1 | A | 1A | 1A4 | % Complete | 2020-02-29 | Material | CAM A | 375000.001 | 0.001 | 0.001 | 375000.001
1 | A | 1A | 1A4 | % Complete | 2020-04-30 | Material | CAM A | 375000.001 | 0.001 | 0.001 | 375000.001
1 | A | 1A | 1A5 | % Complete | 2019-06-30 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A | 1A5 | % Complete | 2019-07-31 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A | 1A5 | % Complete | 2019-08-31 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A | 1A5 | % Complete | 2019-09-30 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A | 1A5 | % Complete | 2019-10-31 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A | 1A5 | % Complete | 2019-11-30 | Material | CAM A | 175000.001 | 175000.001 | 0.001 | 0.001
1 | A | 1A |  |  | 2019-05-31 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-06-30 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-06-30 | Material | CAM A | 0.001 | 0.001 | 175000.001 | 0.001
1 | A | 1A |  |  | 2019-07-31 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-07-31 | Material | CAM A | 0.001 | 0.001 | 175000.001 | 0.001
1 | A | 1A |  |  | 2019-08-31 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-08-31 | Material | CAM A | 0.001 | 0.001 | 175000.001 | 0.001
1 | A | 1A |  |  | 2019-09-30 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-09-30 | Material | CAM A | 0.001 | 0.001 | 175000.001 | 0.001
1 | A | 1A |  |  | 2019-10-31 | Labor | CAM A | 0.001 | 0.001 | 50000.001 | 0.001
1 | A | 1A |  |  | 2019-10-31 | Material | CAM A | 0.001 | 0.001 | 800000.001 | 0.001
1 | A | 1A |  |  | 2019-11-30 | Material | CAM A | 0.001 | 0.001 | 275000.001 | 0.001
1 | A | 1A |  |  | 2019-12-31 | Material | CAM A | 0.001 | 0.001 | 125000.001 | 0.001
1 | B | 1B | 1B1 | % Complete | 2020-04-30 | Labor | CAM B | 37500.001 | 0.001 | 0.001 | 37500.001
1 | B | 1B | 1B1 | % Complete | 2020-05-31 | Labor | CAM B | 75000.001 | 0.001 | 0.001 | 75000.001
1 | B | 1B | 1B1 | % Complete | 2020-06-30 | Labor | CAM B | 37500.001 | 0.001 | 0.001 | 37500.001
1 | B | 1B | 1B2 | % Complete | 2019-12-31 | Labor | CAM B | 25000.001 | 25000.001 | 0.001 | 0.001
1 | B | 1B | 1B2 | % Complete | 2020-01-31 | Labor | CAM B | 225000.001 | 0.001 | 0.001 | 225000.001
1 | B | 1B | 1B3 | % Complete | 2020-01-31 | Labor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
1 | B | 1B | 1B3 | % Complete | 2020-02-29 | Labor | CAM B | 5000.001 | 0.001 | 0.001 | 5000.001
1 | B | 1B | 1B5 | % Complete | 2020-01-31 | Labor | CAM B | 625000.001 | 0.001 | 0.001 | 625000.001
1 | B | 1B | 1B5 | % Complete | 2020-01-31 | Subcontractor | CAM B | 625000.001 | 0.001 | 0.001 | 625000.001
1 | B | 1B | 1B5 | % Complete | 2020-02-29 | Labor | CAM B | 625000.001 | 0.001 | 0.001 | 625000.001
1 | B | 1B | 1B5 | % Complete | 2020-02-29 | Subcontractor | CAM B | 625000.001 | 0.001 | 0.001 | 625000.001
1 | B | 1B | 1B6 | % Complete | 2020-02-29 | Labor | CAM B | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | B | 1B | 1B6 | % Complete | 2020-02-29 | Subcontractor | CAM B | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | B | 1B | 1B6 | % Complete | 2020-03-31 | Labor | CAM B | 1250000.001 | 0.001 | 0.001 | 1250000.001
1 | B | 1B | 1B6 | % Complete | 2020-03-31 | Subcontractor | CAM B | 1250000.001 | 0.001 | 0.001 | 1250000.001
1 | B | 1B | 1B6 | % Complete | 2020-04-30 | Labor | CAM B | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | B | 1B | 1B6 | % Complete | 2020-04-30 | Subcontractor | CAM B | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | B | 1B | 1B6 | % Complete | 2020-05-31 | Labor | CAM B | 750000.001 | 0.001 | 0.001 | 750000.001
1 | B | 1B | 1B6 | % Complete | 2020-05-31 | Subcontractor | CAM B | 750000.001 | 0.001 | 0.001 | 750000.001
1 | B | 1B | 1B6 | % Complete | 2020-06-30 | Labor | CAM B | 500000.001 | 0.001 | 0.001 | 500000.001
1 | B | 1B | 1B6 | % Complete | 2020-06-30 | Subcontractor | CAM B | 500000.001 | 0.001 | 0.001 | 500000.001
1 | B | 1B | 1B6 | % Complete | 2020-07-31 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
1 | B | 1B | 1B6 | % Complete | 2020-07-31 | Subcontractor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
1 | B | 1B | 1B6 | % Complete | 2020-08-31 | Labor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
1 | B | 1B | 1B6 | % Complete | 2020-08-31 | Subcontractor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
1 | B | 1B |  |  | 2019-12-31 | Labor | CAM B | 0.001 | 0.001 | 25000.001 | 0.001
1 | C | 1C | 1C3 | % Complete | 2019-11-30 | Subcontractor | CAM C | 992500.001 | 992500.001 | 0.001 | 0.001
1 | C | 1C | 1C3 | % Complete | 2019-12-31 | Subcontractor | CAM C | 1000000.001 | 1000000.001 | 0.001 | 0.001
1 | C | 1C | 1C3 | % Complete | 2020-01-31 | Subcontractor | CAM C | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | C | 1C | 1C4 | % Complete | 2019-05-31 | Subcontractor | CAM C | 250000.001 | 250000.001 | 0.001 | 0.001
1 | C | 1C | 1C4 | % Complete | 2019-06-30 | Subcontractor | CAM C | 500000.001 | 500000.001 | 0.001 | 0.001
1 | C | 1C | 1C4 | % Complete | 2019-07-31 | Subcontractor | CAM C | 750000.001 | 750000.001 | 0.001 | 0.001
1 | C | 1C | 1C4 | % Complete | 2019-08-31 | Subcontractor | CAM C | 750000.001 | 750000.001 | 0.001 | 0.001
1 | C | 1C |  |  | 2019-05-31 | Subcontractor | CAM C | 0.001 | 0.001 | 250000.001 | 0.001
1 | C | 1C |  |  | 2019-06-30 | Subcontractor | CAM C | 0.001 | 0.001 | 500000.001 | 0.001
1 | C | 1C |  |  | 2019-07-31 | Subcontractor | CAM C | 0.001 | 0.001 | 750000.001 | 0.001
1 | C | 1C |  |  | 2019-08-31 | Subcontractor | CAM C | 0.001 | 0.001 | 750000.001 | 0.001
1 | C | 1C |  |  | 2019-11-30 | Subcontractor | CAM C | 0.001 | 0.001 | 992500.001 | 0.001
1 | C | 1C |  |  | 2019-12-31 | Subcontractor | CAM C | 0.001 | 0.001 | 1000000.001 | 0.001
1 | D | 1D | 1D1 | PP | 2020-02-29 | Labor | CAM D | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | D | 1D | 1D1 | PP | 2020-02-29 | Material | CAM D | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | D | 1D | 1D1 | PP | 2020-02-29 | Other Direct Costs | CAM D | 87500.001 | 0.001 | 0.001 | 87500.001
1 | D | 1D | 1D1 | PP | 2020-04-30 | Labor | CAM D | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | D | 1D | 1D1 | PP | 2020-04-30 | Material | CAM D | 1000000.001 | 0.001 | 0.001 | 1000000.001
1 | D | 1D | 1D1 | PP | 2020-04-30 | Other Direct Costs | CAM D | 87500.001 | 0.001 | 0.001 | 87500.001
1 | D | 1D | 1D2 | PP | 2020-05-31 | Material | CAM D | 2000000.001 | 0.001 | 0.001 | 2000000.001
1 | D | 1D | 1D2 | PP | 2020-11-30 | Material | CAM D | 1750000.001 | 0.001 | 0.001 | 1750000.001
1 | D | 1D | 1D2 | PP | 2020-12-31 | Material | CAM D | 5000000.001 | 0.001 | 0.001 | 5000000.001
2 | A | 2A | 2A1 | 0/100 | 2020-05-31 | Material | CAM A | 125000.001 | 0.001 | 0.001 | 125000.001
2 | A | 2A | 2A2 | 50/50 | 2020-01-31 | Material | CAM A | 100000.001 | 0.001 | 0.001 | 100000.001
2 | A | 2A | 2A2 | 50/50 | 2020-02-29 | Material | CAM A | 100000.001 | 0.001 | 0.001 | 100000.001
2 | A | 2A | 2A3 | % Complete | 2019-07-31 | Material | CAM A | 62500.001 | 62500.001 | 0.001 | 0.001
2 | A | 2A | 2A3 | % Complete | 2019-08-31 | Material | CAM A | 125000.001 | 125000.001 | 0.001 | 0.001
2 | A | 2A | 2A3 | % Complete | 2019-09-30 | Material | CAM A | 62500.001 | 62500.001 | 0.001 | 0.001
2 | A | 2A | 2A3 | % Complete | 2019-10-31 | Material | CAM A | 125000.001 | 125000.001 | 0.001 | 0.001
2 | A | 2A | 2A3 | % Complete | 2019-11-30 | Material | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
2 | A | 2A | 2A3 | % Complete | 2019-12-31 | Material | CAM A | 125000.001 | 125000.001 | 0.001 | 0.001
2 | A | 2A | 2A4 | 50/50 | 2020-04-30 | Labor | CAM A | 75000.001 | 0.001 | 0.001 | 75000.001
2 | A | 2A | 2A4 | 50/50 | 2020-05-31 | Labor | CAM A | 75000.001 | 0.001 | 0.001 | 75000.001
2 | A | 2A |  |  | 2019-07-31 | Material | CAM A | 0.001 | 0.001 | 62500.001 | 0.001
2 | A | 2A |  |  | 2019-08-31 | Material | CAM A | 0.001 | 0.001 | 125000.001 | 0.001
2 | A | 2A |  |  | 2019-09-30 | Material | CAM A | 0.001 | 0.001 | 62500.001 | 0.001
2 | A | 2A |  |  | 2019-10-31 | Material | CAM A | 0.001 | 0.001 | 125000.001 | 0.001
2 | A | 2A |  |  | 2019-11-30 | Material | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
2 | A | 2A |  |  | 2019-12-31 | Material | CAM A | 0.001 | 0.001 | 125000.001 | 0.001
2 | B | 2B | 2B1 | 0/100 | 2020-03-31 | Other Direct Costs | CAM B | 25000.001 | 0.001 | 0.001 | 25000.001
2 | B | 2B | 2B4 | 0/100 | 2019-11-30 | Material | CAM B | 100000.001 | 100000.001 | 0.001 | 0.001
2 | B | 2B |  |  | 2019-11-30 | Material | CAM B | 0.001 | 0.001 | 100000.001 | 0.001
2 | C | 2C | 2C1 | PP | 2020-02-29 | Subcontractor | CAM C | 400000.001 | 0.001 | 0.001 | 400000.001
2 | C | 2C | 2C1 | PP | 2020-02-29 | Labor | CAM C | 300000.001 | 0.001 | 0.001 | 300000.001
2 | C | 2C | 2C1 | PP | 2020-03-31 | Subcontractor | CAM C | 625000.001 | 0.001 | 0.001 | 625000.001
2 | C | 2C | 2C1 | PP | 2020-03-31 | Labor | CAM C | 500000.001 | 0.001 | 0.001 | 500000.001
2 | C | 2C | 2C1 | PP | 2020-04-30 | Subcontractor | CAM C | 250000.001 | 0.001 | 0.001 | 250000.001
2 | C | 2C | 2C1 | PP | 2020-04-30 | Labor | CAM C | 375000.001 | 0.001 | 0.001 | 375000.001
3 | C | 3C | 3C1 | % Complete | 2019-11-30 | Subcontractor | CAM C | 25000.001 | 25000.001 | 0.001 | 0.001
3 | C | 3C | 3C1 | % Complete | 2019-12-31 | Subcontractor | CAM C | 230000.001 | 230000.001 | 0.001 | 0.001
3 | C | 3C | 3C1 | % Complete | 2020-01-31 | Subcontractor | CAM C | 25000.001 | 0.001 | 0.001 | 25000.001
3 | C | 3C | 3C2 | % Complete | 2019-12-31 | Subcontractor | CAM C | 75000.001 | 75000.001 | 0.001 | 0.001
3 | C | 3C | 3C2 | % Complete | 2020-01-31 | Subcontractor | CAM C | 300000.001 | 0.001 | 0.001 | 300000.001
3 | C | 3C | 3C2 | % Complete | 2020-02-29 | Subcontractor | CAM C | 150000.001 | 0.001 | 0.001 | 150000.001
3 | C | 3C | 3C3 | % Complete | 2020-02-29 | Subcontractor | CAM C | 125000.001 | 0.001 | 0.001 | 125000.001
3 | C | 3C | 3C3 | % Complete | 2020-03-31 | Subcontractor | CAM C | 125000.001 | 0.001 | 0.001 | 125000.001
3 | C | 3C | 3C3 | % Complete | 2020-04-30 | Subcontractor | CAM C | 250000.001 | 0.001 | 0.001 | 250000.001
3 | C | 3C | 3C3 | % Complete | 2020-06-30 | Subcontractor | CAM C | 62500.001 | 0.001 | 0.001 | 62500.001
3 | C | 3C |  |  | 2019-11-30 | Subcontractor | CAM C | 0.001 | 0.001 | 25000.001 | 0.001
3 | C | 3C |  |  | 2019-12-31 | Subcontractor | CAM C | 0.001 | 0.001 | 305000.001 | 0.001
4 | B | 4B | 4B1 | PP | 2020-02-29 | Material | CAM B | 2500000.001 | 0.001 | 0.001 | 2500000.001
4 | C | 4C | 4C1 | PP | 2020-02-29 | Subcontractor | CAM C | 5000000.001 | 0.001 | 0.001 | 5000000.001
4 | D | 4D | 4D1 | 0/100 | 2019-12-31 | Labor | CAM D | 1000000.001 | 1000000.001 | 0.001 | 0.001
4 | D | 4D | 4D1 | 0/100 | 2019-12-31 | Other Direct Costs | CAM D | 125000.001 | 125000.001 | 0.001 | 0.001
4 | D | 4D | 4D1 | 0/100 | 2019-12-31 | Subcontractor | CAM D | 4750000.001 | 4750000.001 | 0.001 | 0.001
4 | D | 4D | 4D2 | 0/100 | 2020-01-31 | Material | CAM D | 3000000.001 | 0.001 | 0.001 | 3000000.001
4 | D | 4D | 4D3 | PP | 2020-03-31 | Labor | CAM D | 125000.001 | 0.001 | 0.001 | 125000.001
4 | D | 4D | 4D3 | PP | 2020-03-31 | Other Direct Costs | CAM D | 125000.001 | 0.001 | 0.001 | 125000.001
4 | D | 4D | 4D3 | PP | 2020-04-30 | Labor | CAM D | 1125000.001 | 0.001 | 0.001 | 1125000.001
4 | D | 4D |  |  | 2019-12-31 | Labor | CAM D | 0.001 | 0.001 | 1000000.001 | 0.001
4 | D | 4D |  |  | 2019-12-31 | Other Direct Costs | CAM D | 0.001 | 0.001 | 125000.001 | 0.001
4 | D | 4D |  |  | 2019-12-31 | Subcontractor | CAM D | 0.001 | 0.001 | 4750000.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-05-31 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-06-30 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-07-31 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-08-31 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-09-30 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-10-31 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-11-30 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A1 | LOE | 2019-12-31 | Labor | CAM A | 250000.001 | 250000.001 | 0.001 | 0.001
5 | A | 5A | 5A2 | LOE | 2020-01-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-02-29 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-03-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-04-30 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-05-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-06-30 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-07-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-08-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-09-30 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-10-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-11-30 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A | 5A2 | LOE | 2020-12-31 | Labor | CAM A | 250000.001 | 0.001 | 0.001 | 250000.001
5 | A | 5A |  |  | 2019-05-31 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-06-30 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-07-31 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-08-31 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-09-30 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-10-31 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-11-30 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | A | 5A |  |  | 2019-12-31 | Labor | CAM A | 0.001 | 0.001 | 250000.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-05-31 | Labor | CAM B | 50000.001 | 50000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-06-30 | Labor | CAM B | 50000.001 | 50000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-07-31 | Labor | CAM B | 50000.001 | 50000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-08-31 | Labor | CAM B | 50000.001 | 50000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-09-30 | Labor | CAM B | 75000.001 | 75000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-10-31 | Labor | CAM B | 75000.001 | 75000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-11-30 | Labor | CAM B | 75000.001 | 75000.001 | 0.001 | 0.001
5 | B | 5B | 5B1 | LOE | 2019-12-31 | Labor | CAM B | 75000.001 | 75000.001 | 0.001 | 0.001
5 | B | 5B | 5B2 | LOE | 2020-01-31 | Labor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
5 | B | 5B | 5B2 | LOE | 2020-02-29 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-03-31 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-04-30 | Labor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
5 | B | 5B | 5B2 | LOE | 2020-05-31 | Labor | CAM B | 125000.001 | 0.001 | 0.001 | 125000.001
5 | B | 5B | 5B2 | LOE | 2020-06-30 | Labor | CAM B | 200000.001 | 0.001 | 0.001 | 200000.001
5 | B | 5B | 5B2 | LOE | 2020-07-31 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-08-31 | Labor | CAM B | 200000.001 | 0.001 | 0.001 | 200000.001
5 | B | 5B | 5B2 | LOE | 2020-09-30 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-10-31 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-11-30 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B | 5B2 | LOE | 2020-12-31 | Labor | CAM B | 250000.001 | 0.001 | 0.001 | 250000.001
5 | B | 5B |  |  | 2019-05-31 | Labor | CAM B | 0.001 | 0.001 | 50000.001 | 0.001
5 | B | 5B |  |  | 2019-06-30 | Labor | CAM B | 0.001 | 0.001 | 50000.001 | 0.001
5 | B | 5B |  |  | 2019-07-31 | Labor | CAM B | 0.001 | 0.001 | 50000.001 | 0.001
5 | B | 5B |  |  | 2019-08-31 | Labor | CAM B | 0.001 | 0.001 | 50000.001 | 0.001
5 | B | 5B |  |  | 2019-09-30 | Labor | CAM B | 0.001 | 0.001 | 75000.001 | 0.001
5 | B | 5B |  |  | 2019-10-31 | Labor | CAM B | 0.001 | 0.001 | 75000.001 | 0.001
5 | B | 5B |  |  | 2019-11-30 | Labor | CAM B | 0.001 | 0.001 | 75000.001 | 0.001
5 | B | 5B |  |  | 2019-12-31 | Labor | CAM B | 0.001 | 0.001 | 75000.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-05-31 | Labor | CAM C | 125000.001 | 125000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-06-30 | Labor | CAM C | 125000.001 | 125000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-07-31 | Labor | CAM C | 125000.001 | 125000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-08-31 | Labor | CAM C | 125000.001 | 125000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-09-30 | Labor | CAM C | 200000.001 | 200000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-10-31 | Labor | CAM C | 250000.001 | 250000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-11-30 | Labor | CAM C | 200000.001 | 200000.001 | 0.001 | 0.001
5 | C | 5C | 5C1 | LOE | 2019-12-31 | Labor | CAM C | 125000.001 | 125000.001 | 0.001 | 0.001
5 | C | 5C | 5C2 | LOE | 2020-01-31 | Labor | CAM C | 100000.001 | 0.001 | 0.001 | 100000.001
5 | C | 5C | 5C2 | LOE | 2020-02-29 | Labor | CAM C | 125000.001 | 0.001 | 0.001 | 125000.001
5 | C | 5C | 5C2 | LOE | 2020-03-31 | Labor | CAM C | 150000.001 | 0.001 | 0.001 | 150000.001
5 | C | 5C | 5C2 | LOE | 2020-04-30 | Labor | CAM C | 175000.001 | 0.001 | 0.001 | 175000.001
5 | C | 5C | 5C2 | LOE | 2020-05-31 | Labor | CAM C | 200000.001 | 0.001 | 0.001 | 200000.001
5 | C | 5C | 5C2 | LOE | 2020-06-30 | Labor | CAM C | 225000.001 | 0.001 | 0.001 | 225000.001
5 | C | 5C | 5C2 | LOE | 2020-07-31 | Labor | CAM C | 250000.001 | 0.001 | 0.001 | 250000.001
5 | C | 5C | 5C2 | LOE | 2020-08-31 | Labor | CAM C | 225000.001 | 0.001 | 0.001 | 225000.001
5 | C | 5C | 5C2 | LOE | 2020-09-30 | Labor | CAM C | 200000.001 | 0.001 | 0.001 | 200000.001
5 | C | 5C | 5C2 | LOE | 2020-10-31 | Labor | CAM C | 175000.001 | 0.001 | 0.001 | 175000.001
5 | C | 5C | 5C2 | LOE | 2020-11-30 | Labor | CAM C | 150000.001 | 0.001 | 0.001 | 150000.001
5 | C | 5C | 5C2 | LOE | 2020-12-31 | Labor | CAM C | 125000.001 | 0.001 | 0.001 | 125000.001
5 | C | 5C |  |  | 2019-05-31 | Labor | CAM C | 0.001 | 0.001 | 125000.001 | 0.001
5 | C | 5C |  |  | 2019-06-30 | Labor | CAM C | 0.001 | 0.001 | 125000.001 | 0.001
5 | C | 5C |  |  | 2019-07-31 | Labor | CAM C | 0.001 | 0.001 | 125000.001 | 0.001
5 | C | 5C |  |  | 2019-08-31 | Labor | CAM C | 0.001 | 0.001 | 125000.001 | 0.001
5 | C | 5C |  |  | 2019-09-30 | Labor | CAM C | 0.001 | 0.001 | 200000.001 | 0.001
5 | C | 5C |  |  | 2019-10-31 | Labor | CAM C | 0.001 | 0.001 | 250000.001 | 0.001
5 | C | 5C |  |  | 2019-11-30 | Labor | CAM C | 0.001 | 0.001 | 200000.001 | 0.001
5 | C | 5C |  |  | 2019-12-31 | Labor | CAM C | 0.001 | 0.001 | 125000.001 | 0.001
5 | D | 5D | 5D1 | LOE | 2020-01-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-02-29 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-03-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-04-30 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-05-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-06-30 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-07-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-08-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-09-30 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-10-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-11-30 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
5 | D | 5D | 5D1 | LOE | 2020-12-31 | Labor | CAM D | 375000.001 | 0.001 | 0.001 | 375000.001
6 | D | 6D | 6D1 | 0/100 | 2020-12-31 | Material | CAM D | 500000.001 | 0.001 | 0.001 | 500000.001
6 | D | 6D | 6D2 | 50/50 | 2020-11-30 | Material | CAM D | 500000.001 | 0.001 | 0.001 | 500000.001
6 | D | 6D | 6D2 | 50/50 | 2020-12-31 | Material | CAM D | 500000.001 | 0.001 | 0.001 | 500000.001
6 | D | 6D | 6D3 | 0/100 | 2019-10-31 | Material | CAM D | 500000.001 | 500000.001 | 0.001 | 0.001
6 | D | 6D |  |  | 2019-10-31 | Material | CAM D | 0.001 | 0.001 | 500000.001 | 0.001